 

Material made with the financial support of the European Commission. The content of this material is the sole responsibility of the authors, and the National Agency and the European Commission are

**IMPLEMENTATION PLAN**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Current activity number** | **The period of**  **implementation** | **Activity Description** | **Participants** | **Results** |
| 1. | 09.2020 | Selecting participants and establishing the tasks of the project team | All the countries | * Appointment decisions * Partnership agreements |
| 2. | 09.2020 | Organizing a meeting with parents to promote the project | All the countries | * Participation lists |
| 3. | 09.2020 | Creating a communication network between partner kindergartens | Turkey | * WhatsApp group |
| 4. | 09.2020 | Organizing and elaborating a planning for the activities within the Erasmus + Club | All the countries | * Erasmus Corner * Activity planning |
| 5. | 09.2020 | Promoting the project on the sites of the partner kindergartens | All the countries | * Posts in the online environment |
| 6. | 10.2020 | Elaboration and application of direct observation sheets in the field of social skills (children) and questionnaires regarding transversal competences (teachers) | Development-Romania  Application - all countries | * Direct observation sheets * Questionnaires |
| 7. | 10.2020 | Creating an official page on Facebook and ETwinning | Romania  North Macedonia | * Facebook account * Etwinning account |
| 8. | 10.2020 | Erasmus Club activity 1 | All the countries | * Various products |
| 9. | 11.2020 | Organizing a meeting with the teachers from the unit to establish the participants in the mobilities. | All the countries | * Selection procedure * Lists of candidates |
| 10. | 11.2020 | Update web pages | All the countries | * Posts, photos, videos, * Comments, descriptions |
| 11. | 12.2020 | Organizing an artistic cultural event with parents and children to promote the culture of the partner countries | All the countries | * Attendance lists * Pictures |
| 12. | 12.2020 | Update web pages | All the countries | * Posts, photos, videos, * Comments, descriptions |
| 13. | 01.2021 | Erasmus Club activity 2 | All the countries | * Various products |
| 14. | 01.2021 | Update web pages | All the countries | * Posts, photos, videos, * Comments, descriptions |
| 15. | 02.2021 | Creating banners for publishing the project in the community | All the countries | * Banner |
| 16. | 02.2021 | Preparation of materials and documents for Mobility 1 | Romania | * • Info-pack (cultural and social details / materials about methods and strategies used in class * Didactic materials * Mobility agenda * Presentation ppt * Certificates of participation * Feedback sheet |
| 17. | 03. 2021 | Preparing logistics for travel | North Macedonia  Turcia | * Asigurari storno * Bilete de calatorie * Rezervare cazare si masa |
| 18. | 04.2021 | DEVELOPMENT OF MOBILITY 1 | Romania- g  Turcia-participant  North Macedonia-participant |  |
| 19. | 05.2021 | Organization of a Workshop with the teachers from the unit for the dissemination of the activities carried out in mobility in Romania | Turkey  North Macedonia | * Certificates of participation for the participating teachers |
| 20. | 05.2020 | Applying new methods learned in class | Turkey  North Macedonia | * Sheets for monitoring the activity of teachers in the classroom |
| 21. | 05.2021 | Organizing a workshop with parents and children | Turkey  North Macedonia | * Educational products * List of participants * pictures |
| 22. | 06.2021 | Erasmus Club activity 3 | All the countries | * Various products |
| 23. | 06.2021 | Update web pages | All the countries | * Posts * Comments * Materials used in Mobility |
| 24. | 09.2021 | Preparation of materials and documents for Mobility 2 | North Macedonia | * Info-pack (cultural and social details / materials about methods and strategies used in class * Didactic materials * Mobility agenda * Presentation ppt * Certificates of participation * Feedback sheet |
| 25. | 09.2021 | Preparing logistics for travel | Romania  Turkey | * Cancellation insurance * Travel tickets * Accommodation and meal reservation |
| 26. | 10.2021 | DEVELOPMENT OF MOBILITY 2 | North Macedonia host  Romania-participant  Turkey-participant |  |
| 27. | 11.2021 | Organizing a Team-Building for the dissemination of the activities completed in Mobility 2 as teachers in the unit | Romania | * Certificates of participation * Pictures |
| 28. | 11.2021 | Organizing a Training in which the activities completed in Mobilitae 2 will be disseminated with the teachers from the unit. | Turkey | * Certificates of participation * Pictures |
| 29. | 11.2021 | Applying new methods learned in class | Romania  Turkey | * Class activity monitoring sheet |
| 30. | 12.2021 | Organizing a Focus group with parents on inclusion topics | Romania Turkey | * Participation lists * Pictures * Debate material |
| 31. | 01.2022 | Performing activity Erasme Club 4 | All the countries | * Various products |
| 32. | 02.2022 | Update web pages | All the countries | * Posts, photos, videos, * Comments, descriptions |
| 33. | 03.2022 | Preparation of materials and documents for Mobility 3 | Turkey | • Info-pack (cultural and social details / materials about methods and strategies used in class  •Didactic materials  • Mobility agenda  • Presentation ppt  • Certificates of participation  • Feedback sheet |
| 34. | 03.2022 | Preparing logistics for travel | Romania North Macedonia | * Cancellation insurance * Travel tickets * Accommodation and meal reservation |
| 35. | 04.2022 | DEVELOPMENT OF MOBILITY 3 | Turkey host  Romania-participant  North Macedonia participant | • List of participants  • Certificates of participation  • Pictures   * Presentation material |
| 36. | 05.2022 | Elaboration and distribution of leaflets in the community | All the countries | * Number of leaflets distributed |
| 37. | 05.2022 | Applying new methods learned in class | Romania  Macedonia | * Class activity monitoring sheet |
| 38. | 05.2022 | Organizing REGIONAL WORKSHOP with community teachers | Romania | * List of participants * Certificates of participation * Pictures * Presentation material |
| 39. | 05.2022 | Organizing a SEMINAR - topics of inclusion with the community (invited a Parenting Consultant) | Romania | * Lists of participants * Pictures |
| 40. | 05.2022 | Organizing an Exhibition with symbolic products created within the Erasmus + Club | North Macedonia | * Pictures |
| 41. | 06.2022 | Update web pages | All the countries | * Posts * Comments |
| 42. | 06.2022 | Final application of direct observation sheets for children and interpretation of results | All the countries | * Summary |
| 43. | 06.2022 | Elaboration and application of Impact Questionnaires to parents from participating Institutions | All the countries | * Summary |
| 44. | 06.2022 | Final application of the Questionnaires for teachers and interpretation of results | All the countries | * Summary |
| 45. | 06.2022 | Elaboration of the Guide of good practices | Romania | * Guide |
| 46. | 07.2022 | Translation, distribution to partners of the guide of good practices | Romania | * Translated guide |
| 47. | 07.2022 | Uploading various materials on the ACTIVITIES KINDERGARTEN Facebook page | Romania | * Posts, material uploads |
| 48. | 08.2022 | Elaboration of the Final Report | All the countries | * Final report |